## Requirements Register
ID | Requirement Name | Detailed Requirement | Category | Applicable Scope | Requested By | Priority | Business Value / Rationale | Acceptance Criteria | Current Assessment | SystemPrompt Fit | Gap / Action Required | Owner | Status | Validation Method | Documentation Reference | Notes | Ed's comments | Evidence (replication) | Related decision | Delivered on
REQ-001 | Admin User Management | Provide authorized administrators with the ability to manage SystemPrompt users directly from the Admin UI, including viewing/searching, creating, updating, disabling/deleting users, assigning roles, viewing last login, and revoking sessions. | Identity & Access | Enterprise / Core / Commerce | Andrew Nagornyy | P0 – Critical | Centralized administration is required before SystemPrompt can move beyond a controlled evaluation environment. | Admin can search/list users, create users, modify role/status, disable/delete access, review basic account activity, and revoke sessions without CLI or database access. | Partial | Backend/CLI capability appears available; Admin UI exposure needs validation. | Confirm current Admin UI capability and expose/enable existing user-management functions. | SystemPrompt | Delivered | Admin UI functional test + role-based access test | https://astound.systemprompt.io/documentation/enterprise-user-access | Initial stakeholder requirement. ¦ Evidence: tagged Playwright specs + screenshot pack; replication commands on the docs page. | Delivered - full user CRUD, roles, disable/delete, invites, session + PAT revocation, all from the Admin UI; three security defects fixed alongside. Please run acceptance testing against the live deployment. | just e2e -- --grep @REQ-001 |  | 2026-08-25
REQ-002 | Controlled User Registration | Prevent unrestricted self-registration. Only approved users should be eligible to create/use SystemPrompt accounts and connect a Bridge. | Security / IAM | Enterprise / Core / Commerce | Andrew Nagornyy | P0 – Critical | Open registration is an enterprise access-control risk and must be hardened before broader rollout. | An unapproved user cannot create an account or connect a Bridge. Approved/provisioned users can access the platform based on assigned entitlements. | Requires configuration / validation | Authentication and role controls exist; enterprise enrolment policy is not clearly documented. | Define and implement closed enrolment; confirm admin provisioning, allowlists, SSO/domain restrictions, or equivalent controls. | SP + Astound | Delivered | Negative registration test + approved-user onboarding test | https://astound.systemprompt.io/documentation/enterprise-user-access | Current dev setup allows self-registration for testing. ¦ Trade accepted per the requirement: every new user needs an admin invite. Open question: should Bridge device-link also need per-device admin approval? | Delivered - all three self-registration doors are closed (core registration flag, passkey self-reg, SSO auto-provision); admin invite (single-use, 7-day TTL) is the only path in. Test: an unapproved address gets nowhere. | just e2e -- --grep @REQ-002 |  | 2026-08-25
REQ-003 | Usage Analytics Dashboard | Provide an Admin dashboard showing SystemPrompt usage trends, request volumes, active users, and daily/weekly activity. | Analytics | Enterprise / Core / Commerce | Andrew Nagornyy | P1 – High | Required to understand platform adoption, operational usage, and overall utilization. | Dashboard shows daily/weekly requests, total request volume, active users, and historical usage trends with selectable time periods. | Partial / likely supported | Analytics capability is documented, but required views are not visible in the current Astound deployment. | Confirm deployment/version/configuration and expose the documented analytics in the Admin UI. | SystemPrompt | Delivered | Admin dashboard review + API/CLI cross-check | https://astound.systemprompt.io/documentation/enterprise-analytics | Custom windows are capped at 30 days for query cost; tell us if quarter/year views are required. | Delivered - 5-tab dashboard with daily/weekly series, active users, selectable windows (15m-30d + custom). | just e2e -- --grep @REQ-003 |  | 2026-08-25
REQ-004 | AI Cost & Model Analytics | Provide visibility into total AI spend, daily cost trends, cost per request, request counters, and AI model usage distribution. | FinOps / Analytics | Enterprise / Core / Commerce | Andrew Nagornyy | P1 – High | Enables cost governance, model optimization, and identification of major cost drivers. | Admin can see total spend, spend trend, cost/request, token/request activity, and usage distribution by AI model. | Partial / likely supported | Core request, token, model, and cost telemetry appears available. | Validate available fields and configure/build the required Admin dashboard visualizations. | SystemPrompt | Delivered | Compare dashboard totals with request/cost telemetry | https://astound.systemprompt.io/documentation/enterprise-cost-management | Reconcile dashboard totals against the CLI (analytics costs summary) during acceptance. | Delivered - total spend, daily trend, cost/request, tokens, model distribution, month-end P&L by org/provider/model. Costs are integer microdollars end to end. | just e2e -- --grep @REQ-004 |  | 2026-08-25
REQ-005 | User Adoption & Utilization Analytics | Provide user-level analytics including active seats/users, weekly active users, requests per user/day, top users, and users with zero requests over a configurable period such as 30 days. | Adoption Analytics | Enterprise / Core / Commerce | Andrew Nagornyy | P1 – High | Allows identification of adoption gaps, under-utilized access, and potentially wasted seats/capacity. | Admin can report WAU, requests/user/day, top users, and inactive users over a configurable period. | Partial | Underlying user-attributed request data appears available; some KPIs are likely derived rather than standard widgets. | Validate available reporting and add derived widgets/queries where required. | SystemPrompt | Delivered | User-level analytics reconciliation against raw request logs | https://astound.systemprompt.io/documentation/enterprise-analytics | Provisioned but never used' is now distinguishable from 'used on day one'. | Delivered - WAU with deltas, requests/user/day, top-user leaderboard, inactive seats with a configurable window (7/14/30/90d picker). | just e2e -- --grep @REQ-005 |  | 2026-08-25
REQ-006 | Organizational Analytics Drill-Down | Allow usage, cost, and adoption analytics to be filtered and aggregated by team/group, individual user, Hub, and potentially project. | Enterprise Analytics | Enterprise / Core / Commerce | Andrew Nagornyy | P1 – High | Astound needs to compare usage and cost across Core, Commerce, projects, teams, and individual users. | Admin can filter and aggregate analytics by organizational dimension and drill down to user-level detail. | Gap / unclear | User attribution exists, but an enterprise organizational hierarchy is not clearly documented. | Confirm native metadata dimensions; if missing, define Hub/project/team metadata and reporting model. | SP + Astound | Blocked | Metadata model test + filtered analytics validation | https://astound.systemprompt.io/documentation/enterprise-analytics | DECISION NEEDED (blocks this row plus 010/013/033 full scope): Ed has proposed Hub = geographic grouping, but we need Astound to STRONGLY DEFINE the hierarchy - what a Hub is, and concrete examples of teams and projects inside a Hub, expressed as a data structure we can model (does a user belong to one team or many? does a project grant access or is it only a reporting label? how do Hub/team/project nest under an organization?). Send 2-3 real examples from Core/Commerce and we will design the schema against them. | Partially delivered - org, department and individual-user drill-down work identically across every dashboard. Hub/team/project do not exist yet as dimensions. | just e2e -- --grep @REQ-006 | DEC-001
REQ-007 | AI Development Productivity Metrics | Track engineering-specific metrics such as AI suggestion/Tab acceptance rate, total AI accepts, AI-generated LOC versus manual LOC, and related development activity. | Engineering Analytics | Core / Commerce Engineering | Andrew Nagornyy | P2 – Medium | Helps assess measurable engineering impact rather than AI consumption alone. | Required productivity events can be captured, attributed to users/projects, trended over time, and compared with delivery outcomes. | Gap / requires investigation | IDE-level acceptance and AI-versus-manual LOC telemetry is not clearly documented as native gateway telemetry. | Confirm Bridge/IDE telemetry capabilities; otherwise define IDE/SCM telemetry integration. | SP + Engineering | Blocked | IDE event capture test + repository attribution test | https://astound.systemprompt.io/documentation/enterprise-analytics | Tab acceptance benchmark requested by stakeholder should be treated as a metric target, not a native SystemPrompt capability. ¦ Closing this properly needs an IDE-level integration on Astound's side. Related decision: which external platforms hold the activity you want correlated (IDE telemetry, SCM), and what API access we get to them. | Not feasible as specified on this platform: Claude Code emits no accept/reject signal, so tab-acceptance rate has no data source anywhere. What IS delivered: AI-authored lines added/removed, applied edit operations, permission-grant rate - all honestly labelled as proxies, never a synthetic 'AI vs manual' ratio. | just e2e -- --grep @REQ-007 | DEC-002
REQ-008 | Commit Activity Analytics | Provide daily/weekly commit activity alongside AI usage to support correlation between AI consumption and engineering activity. | Engineering Analytics | Core / Commerce Engineering | Andrew Nagornyy | P2 – Medium | Provides contextual engineering activity data when assessing AI adoption and productivity. | Commit activity can be viewed for the same user/team/project/time period as SystemPrompt AI usage. | Not native / integration likely | Commit data originates from Git/SCM systems rather than the AI gateway. | Integrate GitHub/Bitbucket/Git telemetry or ingest commit metrics into the analytics layer. | SP + Astound | Blocked | SCM integration test + identity matching validation | https://astound.systemprompt.io/documentation/enterprise-analytics | Commit count should be contextual, not used as a standalone productivity KPI. ¦ DECISION NEEDED: name the authoritative SCM (GitHub? Bitbucket? GitLab?) and the identity mapping rule (SCM login / commit-author email -> platform user), plus API/webhook access. Ingest is ~1 week once decided; the identity mapping is the hard part and pairs with the IdP decision on REQ-023. | Partially delivered - commits made through Claude Code sessions are captured, deduped, rolled up daily and plotted beside AI usage over the same window/scope. Commits from plain terminals or CI are invisible. | just e2e -- --grep @REQ-008 | DEC-002
REQ-009 | Spend Limits & Budget Monitoring | Display proximity to defined soft/hard AI spend limits and support monitoring and alerting for budget consumption. | FinOps / Governance | Enterprise / Core / Commerce | Andrew Nagornyy | P1 – High | Prevents uncontrolled AI spend and supports predictable enterprise financial governance. | Admin can see current spend versus budget, threshold utilization, and alerts/actions when configured limits are reached. | Partial | Budget/alert foundations appear available; required scope and granularity need validation. | Validate global versus user/team/project thresholds and define any missing budget-control model. | SP + Astound | Delivered | Threshold alert test + spend-limit enforcement test | https://astound.systemprompt.io/documentation/enterprise-cost-management | Budgets are per-organization today; per-team/project scope awaits the Hub/team definition (REQ-006). | Delivered and enforced, not display-only: hard org monthly cap (429 at the gateway with retry-after at month boundary), soft threshold recorded + Slack-alerted on first crossing, spend meters, burn-up chart, 12-month history. | just e2e -- --grep @REQ-009 |  | 2026-08-25
REQ-010 | Real-Time AI Spend Attribution | As a Business, I shall be able to track AI spend per team, department, product or project in real time for billing accuracy, so that cost is attributed to the correct P&L owner | FinOps / Governance | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Cost is attributed to the correct P&L owner. | For each AI request, cost can be attributed and reported in near real time by an agreed organizational dimension such as team, department, product, project, user, model, and provider. | Supported with metadata caveat | Request/audit data includes user, tenant, model, provider, and cost. Team/department/project attribution requires a reliable custom metadata convention because department is not first-class in current code. | Define required organizational metadata (team/department/product/project) and validate cost attribution end to end. | SP + Astound | Delivered | Cost attribution query + organizational metadata reconciliation | https://astound.systemprompt.io/documentation/enterprise-cost-management | Team/department-as-org-unit/product/project attribution = the same Hub/team data-structure decision as REQ-006. | Delivered for the dimensions that exist: every request is attributed to user, organization, department, model, provider with cost, in near real time. | just e2e -- --grep @REQ-010 | DEC-001 | 2026-08-25
REQ-011 | Spend Overrun Early Warning | As a Business, I shall be able to track AI spend per team, department, product or project in real time for early-warning control, so that budget owners can detect overruns before invoice time when corrective action is no longer possible | FinOps / Governance | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Budget owners can detect overruns before invoice time when corrective action is no longer possible. | Budget owners can identify current spend and receive an actionable early-warning signal before the accounting period closes when spend is trending beyond the expected level. | Partial | Real-time cost data exists, but the source analysis did not find spend-trajectory forecasting or proactive forecast-based notification. | Design/confirm forecast-based budget early-warning logic and notification mechanism. | SP + Astound | Delivered | Simulated budget burn + forecast/alert test | https://astound.systemprompt.io/documentation/enterprise-cost-management | Projection is a linear run-rate and labelled as such; no projection fires in the first 3 days of a month to avoid noise. | Delivered - linear month-end projection computed continuously on the request path; the first projected-overrun crossing per org per month is recorded and Slack-alerted. | just e2e -- --grep @REQ-011 |  | 2026-08-25
REQ-012 | Soft Budget Alerts | As a Business, I shall be able to set and enforce soft budget alerts per team, department, product or project, so that budget owners are notified before a limit is reached without disrupting production service | FinOps / Governance | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Budget owners are notified before a limit is reached without disrupting production service. | A configurable soft threshold can be set for an agreed scope and triggers an alert without blocking production traffic. | Partial | Documentation indicates budget alerts; code confirms quota enforcement, but a non-blocking owner notification path such as email/webhook was not evidenced. | Confirm non-blocking soft alert channels and scope; add email/webhook/dashboard alerting if missing. | SP + Astound | Delivered | Threshold configuration + non-blocking notification test | https://astound.systemprompt.io/documentation/enterprise-cost-management | Alert channel is Slack today; tell us if email/webhook delivery is required and to where. | Delivered - configurable soft threshold per org plan, non-blocking, alert fires on the transition (once), not per request. | just e2e -- --grep @REQ-012 |  | 2026-08-25
REQ-013 | Hard Budget Cutoffs | As a Business, I shall be able to set and enforce hard budget cutoffs per team, department, product or project for non-production-facing workloads, so that no team can create unbudgeted financial exposure for the org | FinOps / Governance | Global / Enterprise | Oleksandr Manatskyi | P2 – Medium | No team can create unbudgeted financial exposure for the org. | A configurable hard threshold can be set for an agreed scope and blocks further eligible AI consumption when the limit is reached. | Partial | Quota windows can enforce request/token ceilings, but the source analysis did not evidence team/project dollar-budget cutoffs. | Define budget scope model and implement dollar-based hard cutoffs where required. | SP + Astound | Delivered | Budget breach + enforcement test | https://astound.systemprompt.io/documentation/enterprise-cost-management | Per-team/project cutoffs need the Hub/team definition (REQ-006). Note quota windows also give a per-user hourly cost ceiling as a runaway backstop. | Delivered at organization scope - dollar-based monthly hard cap, enforced with 429. | just e2e -- --grep @REQ-013 | DEC-001 | 2026-08-25
REQ-014 | Spend Burndown Forecasting | As a Business, I shall be able to receive alerts when spend trajectories exceed forecast before the period closes (burndown forecasting), so that budget owners can intervene mid-cycle rather than discovering overrun retroactively | FinOps / Governance | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Budget owners can intervene mid-cycle rather than discovering overrun retroactively. | The platform projects period-end spend from current burn rate and alerts when projected spend exceeds the configured budget/forecast. | Gap | No period-end spend forecast or burndown projection capability was evidenced. | Add spend forecasting/burndown capability or integrate an external FinOps analytics layer. | SP + Astound | Delivered | Forecast calculation + alert trigger test | https://astound.systemprompt.io/documentation/enterprise-cost-management |  | Delivered together with REQ-011 - burn-up chart plus projection-vs-cap early warning before period close. | just e2e -- --grep @REQ-014 |  | 2026-08-25
REQ-015 | Self-Service Cost Reporting | As a Business, I shall be able to generate self-service, on-demand cost reports sliced by team, department, product, project, model, or provider over any date range, so that budget owners and finance can answer ad hoc spend questions without filing a request to engineering | FinOps / Analytics | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Budget owners and finance can answer ad hoc spend questions without filing a request to engineering. | Authorized users can generate cost reports for any supported date range and slice them by the required organizational and model dimensions without engineering support. | Supported | Cost analytics are queryable by user/tenant/model/provider; organizational slices beyond those dimensions require agreed metadata. | Validate self-service reporting UI/API and required dimensions/date slicing. | SP + Astound | Delivered | Ad hoc report generation across dimensions/date ranges | https://astound.systemprompt.io/documentation/enterprise-cost-management | Slices available: org, department, user, model, provider, date range. Team/project slicing pends REQ-006. | Delivered - CLI reports with arbitrary date ranges + CSV export, and new CSV download endpoints/buttons in the admin web UI (P&L by org/provider/model; usage by user/department/model), org-scoped. | just e2e -- --grep @REQ-015 |  | 2026-08-25
REQ-016 | Scheduled Cost & Budget Digests | As a Business, I shall be able to schedule recurring cost and budget-utilization digests (e.g., weekly, monthly) delivered to budget owners and finance stakeholders, so that spend visibility doesn't depend on someone remembering to check a dashboard | FinOps / Analytics | Global / Enterprise | Oleksandr Manatskyi | P3 – Low | Spend visibility doesn't depend on someone remembering to check a dashboard. | Recurring cost/budget digests can be scheduled and delivered automatically to configured recipients at defined intervals. | Gap / unclear | Recurring scheduled delivery was not evidenced in code and requires confirmation or extension. | Add scheduled digest capability or integrate with reporting/notification tooling. | SP + Astound | Delivered | Scheduled delivery test | https://astound.systemprompt.io/documentation/enterprise-cost-management | Cadence and channel are config; email delivery possible as a follow-up if required. | Delivered - weekly digest job (Monday 08:00 UTC) posting per-org MTD spend vs cap, pace, and trailing-week volume to Slack. | just e2e -- --grep @REQ-016 |  | 2026-08-25
REQ-017 | Provider Cost Comparison | As a Business, I shall be able to compare cost across model providers for quality-normalized equivalent tasks, so that the org can identify savings opportunities | FinOps / Optimization | Global / Enterprise | Oleksandr Manatskyi | P1 – High | The org can identify savings opportunities. | Equivalent workloads can be compared across providers/models using cost and an agreed quality baseline. | Supported | Cost/model/provider dimensions are available. Quality-normalized comparison still requires evaluation/quality data. | Define a quality-normalization method and expose provider/model comparison reporting. | SP + Astound | Blocked | Equivalent-task provider comparison | https://astound.systemprompt.io/documentation/enterprise-cost-management | DECISION NEEDED: 'quality-normalized' comparison is untestable without an agreed quality baseline (an eval set / definition of equivalent tasks). Provide one and we wire the comparison; without it this stays cost-only. | Cost side delivered - provider/model cost + margin breakdown in the internal report and CLI. | just e2e -- --grep @REQ-017 | DEC-005
REQ-018 | Cost / Quality / Latency Model Optimization | As a Business, I shall be able to determine the optimal model for a given task to balance cost/quality/latency trade-offs, so that spend is concentrated on tasks where model capability materially affects outcome quality | FinOps / Optimization | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Spend is concentrated on tasks where model capability materially affects outcome quality. | Routing or recommendations can identify the preferred model for a task using configurable cost, quality, and latency criteria. | Partial | Routing and cost telemetry exist, but no fully automatic optimizer balancing quality, latency, and cost was evidenced. | Define optimization policy and determine whether recommendation/routing logic belongs in SystemPrompt or an evaluation layer. | SP + Astound | Blocked | Routing recommendation / policy test | https://astound.systemprompt.io/documentation/enterprise-model-routing | Blocked on the same quality baseline as REQ-017; once defined we can decide whether recommendation logic lives in the gateway or an eval layer. | Partially delivered - declarative routing on request shape plus a programmatic route-selector seam, with full cost/latency telemetry to decide from. No automatic optimizer. | just e2e -- --grep @REQ-018 | DEC-005
REQ-019 | Tenant-Isolated Semantic Caching | As a Business, I shall be able to eliminate redundant API calls through tenant-isolated semantic caching, so that repeated or near-identical queries reduce cost at volume without leaking one customer's cached data into another's context | FinOps / Optimization | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Repeated or near-identical queries reduce cost at volume without leaking one customer's cached data into another's context. | Repeated or semantically equivalent requests can use a tenant-isolated cache, with no cross-tenant data leakage and measurable cache-hit savings. | Gap | No tenant-isolated semantic cache capability was evidenced in the source analysis. | Evaluate build/integration of a secure tenant-isolated semantic cache. | SP + Astound | Open | Cross-tenant cache-isolation + hit-rate test | https://astound.systemprompt.io/documentation/enterprise-roadmap | A project of its own (~4-6 wks to build: embeddings, per-tenant vector partitions, similarity/invalidation policy, cross-tenant leakage proof). DECISION NEEDED: build vs integrate an existing semantic cache - and confirm the expected traffic actually has enough near-duplicate queries to pay for it. | Not delivered - no semantic cache exists (provider prompt-caching passthrough is not a tenant cache). | just e2e -- --grep @REQ-019
REQ-020 | Model Provider Abstraction | As a Business, I shall be able to abstract application code from any single model provider's API, so that the org retains negotiating leverage and low switching cost rather than facing vendor lock-in | FinOps / Optimization | Global / Enterprise | Oleksandr Manatskyi | P2 – Medium | The org retains negotiating leverage and low switching cost rather than facing vendor lock-in. | Applications use a provider-neutral gateway/API so models/providers can be changed without application-layer rewrites. | Supported | Gateway/provider abstraction is supported and reduces direct provider coupling. | Validate provider substitution with Core/Commerce clients and document the supported compatibility contract. | SP + Astound | Delivered | Provider swap compatibility test | https://astound.systemprompt.io/documentation/enterprise-model-routing |  | Delivered and proven in production - claude-* traffic already redirects to alternate providers with zero application changes. Two inbound API surfaces, four wire protocols, upstream model rewrite. | just e2e -- --grep @REQ-020 |  | 2026-08-25
REQ-021 | Central Model Access Policy | As a Business, I shall be able to define which teams and applications can access which models under which conditions, so that access decisions are centrally auditable and revocable rather than scattered across unmanaged credentials | Identity & Access / Security | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Access decisions are centrally auditable and revocable rather than scattered across unmanaged credentials. | Central policy controls which users/teams/applications may access which models and under what conditions; decisions are auditable and revocable. | Supported with scoping caveat | Central rules/ACLs are evidenced for user/role and governed entities. Team/application policy may require metadata or additional first-class scoping. | Define enterprise access-policy dimensions and close gaps for team/application/project scoping. | SP + Astound | Delivered | RBAC/ACL policy matrix test | https://astound.systemprompt.io/documentation/enterprise-model-routing | Application-level (non-human) scoping rides service accounts today; first-class app identities can be added if a concrete case appears. | Delivered - central per-role/org/department model entitlements enforced at the gateway (403), auditable and revocable, with an admin access-matrix UI. | just e2e -- --grep @REQ-021 |  | 2026-08-25
REQ-022 | Governed Virtual Keys | As a Business, I shall be able to manage virtual keys with budget and rate-limit assignments per team or per customer without exposing raw model provider credentials, so that a leaked or misused key has bounded blast radius | Identity & Access / Security |  | Oleksandr Manatskyi | P1 – High | A leaked or misused key has bounded blast radius. | Administrators can issue revocable virtual credentials with scoped access, rate limits, and budget constraints without exposing provider credentials. | Partial | PATs are revocable and rate tiers exist, but there is no evidenced virtual-key object combining explicit budget and rate-limit assignment. | Decide whether virtual keys are required; if yes, add a credential object with budget/rate-limit policy. | SP + Astound | Blocked | Credential issuance/revocation/rate/budget test | https://astound.systemprompt.io/documentation/enterprise-user-access | DECISION NEEDED - explore the concrete use cases: what are you actually trying to achieve per key? If each application/customer gets its own platform account, today's per-user enforcement already gives per-app budgets and this row is met. If you genuinely need many keys per identity with per-key policy, that is a ~2-week core change. Send the scenarios and we will map adapt-vs-build. | Mostly supported, framing matters: every key is bound to one user, and INDIVIDUAL USER budgets ARE enforced (per-user hourly request + dollar quota at the gateway, org caps above that), so a leaked key can never spend beyond its owner's limits. What does NOT exist is the LiteLLM-style virtual key: one identity holding multiple keys with different budget/rate/model policy per key. | just e2e -- --grep @REQ-022 | DEC-008
REQ-023 | Enterprise SSO Provisioning | As a Business, I shall be able to onboard and offboard access to AI capabilities through the existing identity provider (SSO), not ad-hoc key distribution, so that access management centrally managed | Identity & Access / Security | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Access management centrally managed. | Users are onboarded/offboarded through the enterprise identity provider; access removal in the IdP removes SystemPrompt access without manual key cleanup. | Supported | OAuth2/OIDC with PKCE, WebAuthn, and session/IdP-backed access are evidenced. | Integrate with Astound IdP and validate provisioning/deprovisioning flows. | SP + Astound | Delivered | SSO login + deprovisioning test | https://astound.systemprompt.io/documentation/enterprise-user-access | DECISION NEEDED: confirm the enterprise identity provider going forward - Salesforce? Okta? Entra? GitHub? Today only Salesforce is wired; a different IdP is a new connector (and re-opens SCIM as the right offboarding channel). This decision also drives REQ-007/008: which external platforms hold user activity and how we map their identities to platform users. | Delivered for Salesforce: OIDC+PKCE SSO with gated JIT provisioning, plus a reconciliation job - a user deactivated/removed in Salesforce is disabled here with sessions and PATs revoked (offboarding closes automatically). SCIM deliberately not built: Salesforce does not push standards SCIM and Odoo has none, so an endpoint would have no caller. | just e2e -- --grep @REQ-023 | DEC-002 | 2026-08-25
REQ-024 | Shadow AI Detection & Blocking | As a Business, I shall be able to detect and block unauthorized or shadow AI usage, so that ungoverned model usage doesn't create data leakage, compliance, or cost exposure outside IT/security visibility | Identity & Access / Security | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Ungoverned model usage doesn't create data leakage, compliance, or cost exposure outside IT/security visibility. | Unauthorized or unmanaged AI use can be detected and, where policy requires, blocked or escalated through the governed platform. | Supported | Governance/audit enforcement and managed allowlists provide a foundation for detecting and restricting ungoverned use. | Define detection coverage for direct/non-gateway AI use and determine enforcement controls outside SystemPrompt. | SP + Astound | Delivered | Governed vs ungoverned traffic detection test | https://astound.systemprompt.io/documentation/enterprise-model-routing | Blocking direct provider access (shadow AI off-gateway) is a network/egress control for Astound IT - e.g. egress allow-lists to api.anthropic.com etc. only from the gateway. Happy to advise on the pattern. | Delivered on the governed side - unlisted models are refused, route entitlements enforced, everything audited. Traffic that never touches the gateway cannot be detected from inside the platform. | just e2e -- --grep @REQ-024 |  | 2026-08-25
REQ-025 | Time-Bound External Access | As a Business, I shall be able to grant time-bound or scoped access to specific models for contractors or external teams, so that external access automatically expires without relying on manual revocation discipline | Identity & Access / Security | Global / Enterprise | Oleksandr Manatskyi | P2 – Medium | External access automatically expires without relying on manual revocation discipline. | External/contractor access can be scoped and configured to expire automatically at a defined time without manual revocation. | Partial | Token expiration/revocation exists, but no dedicated scoped time-bound entitlement lifecycle object was evidenced. | Add explicit expiring grants/entitlements if token expiry is insufficient for contractor governance. | SP + Astound | In progress | Timed-access expiry test | https://astound.systemprompt.io/documentation/enterprise-user-access | Tell us the required contractor-access TTL and we enforce a maximum PAT lifetime. Time-bound entitlement rows (grant valid_until) are a small core follow-up if token expiry is not sufficient. | Partially delivered - share links now expire (30-day signed TTL) on top of the existing bounded invites/setup tokens/JWTs; PAT expiry is supported but optional. | just e2e -- --grep @REQ-025
REQ-026 | Immutable AI Audit Trail | As a Business, I shall be able to produce an immutable audit trail of every model call (who, what model, what prompt, when, what was returned), so that the org can reconstruct incidents after the fact or demostrate compliance | Observability / Security | Global / Enterprise | Oleksandr Manatskyi | P1 – High | The org can reconstruct incidents after the fact or demostrate compliance. | Every model call produces an immutable audit record containing actor, time, model/provider, request/response lineage, policy decision, and relevant consumption metadata. | Supported | AI request and governance decision records provide detailed traceable audit data. | Validate retention, immutability, payload protection, and audit export requirements. | SP + Astound | Blocked | Audit completeness + tamper/retention review | https://astound.systemprompt.io/documentation/enterprise-audit-observability | DECISION NEEDED: which compliance regime must this satisfy? That picks the hardening (DB-role REVOKE, hash-chaining, or WORM export) and the retention window. Options are scoped and costed in the design note. | Delivered with a stated caveat: every model call lands a full audit row (actor locked at DB level, model, tokens, cost, latency, trace ids) and governance decisions share the spine. It is append-only by convention, not cryptographically immutable, and ai_requests has no retention policy yet. | just e2e -- --grep @REQ-026 | DEC-007
REQ-027 | End-to-End AI Request Traceability | As a Business, I shall be able to trace end-to-end request flows across model calls, tool invocations, and downstream systems, so that root-cause analysis doesn't require manual log correlation across disconnected systems | Observability / Security | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Root-cause analysis doesn't require manual log correlation across disconnected systems. | A single trace identifier correlates the originating request, model calls, tool/MCP calls, downstream actions, outcomes, and cost. | Supported | Trace IDs correlate inference and tool/MCP execution, enabling end-to-end lineage. | Run trace-lineage tests across model, MCP/tool, and downstream system calls. | SP + Astound | Delivered | Trace propagation / lineage test | https://astound.systemprompt.io/documentation/enterprise-audit-observability |  | Delivered - one trace id correlates request -> policy decision -> model call -> tool execution -> cost, with a universal chain resolver in the admin UI. | just e2e -- --grep @REQ-027 |  | 2026-08-25
REQ-028 | Enterprise Observability Export | As a Business, I shall be able to feed AI telemetry into the existing observability stack (Datadog, Splunk, LGTM) via OTEL as a single standard protocol, so that AI operations are monitored with the same tooling and on-call processes as the rest of production | Observability / Security | Global / Enterprise | Oleksandr Manatskyi | P1 – High | AI operations are monitored with the same tooling and on-call processes as the rest of production. | AI telemetry can be exported into Astound's standard observability/SIEM stack using an agreed supported protocol and mapped into existing monitoring processes. | Partial | Structured SIEM/observability export is evidenced; a distinct OTEL implementation path requires validation. | Confirm OTEL compatibility; otherwise standardize supported JSON/SIEM export integration. | SP + Astound | Blocked | Telemetry export integration test | https://astound.systemprompt.io/documentation/enterprise-audit-observability | DECISION NEEDED: name the target - Datadog, Splunk, or LGTM. Whichever you name gets its exporter built first (~1-2 wks); building all three unprompted is waste. | Partially delivered - OTLP ingest and a live JSON audit stream (SSE) exist; there is no push exporter to an external stack yet. | just e2e -- --grep @REQ-028 | DEC-006
REQ-029 | Model / Use-Case Latency SLOs | As a Business, I shall be able to report on latency SLOs per model and per use case, so that routing and provider decisions are made on measured performance rather than vendor claims | Observability / Security | Global / Enterprise | Oleksandr Manatskyi | P3 – Low | Routing and provider decisions are made on measured performance rather than vendor claims. | Latency can be reported against defined SLOs by model and use case, with sufficient data to compare providers/routes objectively. | Partial | Latency is captured, but use-case SLO definition, thresholding, and SLO-specific reporting are not productized. | Define latency SLOs and add SLO reporting/alerting by model/use-case. | SP + Astound | Delivered | Latency SLO report + threshold test | https://astound.systemprompt.io/documentation/enterprise-audit-observability | Per-use-case SLO taxonomy and error-budget alerting need Astound's SLO definitions - send target latencies per workload class. | Delivered - the latency SLO threshold is configurable (was hardcoded 5s), with breach share reported beside p50/p95 per scope. | just e2e -- --grep @REQ-029 |  | 2026-08-25
REQ-030 | Central Content Safety Guardrails | As a Business, I shall be able to apply consistent content safety guardrails (prompt injection detection, jailbreak attempts, toxic output blocking) regardless of which team built the application, so that security and brand-risk controls aren't dependent on individual team diligence | Observability / Security | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Security and brand-risk controls aren't dependent on individual team diligence. | A centrally managed safety policy is enforced consistently for all governed applications and detects/blocks agreed categories such as prompt injection, jailbreak attempts, secrets, PII, and unsafe output. | Partial | Code evidences jailbreak and limited PII heuristics plus pre-dispatch blocking. Full toxicity/PII taxonomy and response-side blocking are not evidenced. | Define required safety taxonomy and extend prompt/output guardrails beyond current heuristic coverage. | SP + Astound | Testing | Safety adversarial test suite | https://astound.systemprompt.io/documentation/enterprise-safety-guardrails | DECISION NEEDED: sign off the category set - which categories must BLOCK vs audit-only, and is toxicity/brand-risk classification in scope (that needs a classifier, not a heuristic)? We shipped sensible defaults; review them against your policy. | Partially delivered and now ENABLED - jailbreak heuristics, credit-card/SSN detection and secret egress scanning run centrally; ingress blocks, buffered egress blocks, streamed egress is audit-only by design. | just e2e -- --grep @REQ-030 | DEC-003
REQ-031 | AI Usage Anomaly Detection | As a Business, I shall be able to detect anomalies in model usage patterns (volume spikes, unusual prompt structures, cost outliers), so that cost, security, or quality incidents are caught proactively rather than discovered downstream | Observability / Security | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Cost, security, or quality incidents are caught proactively rather than discovered downstream. | The platform detects configured usage anomalies such as volume spikes, error spikes, unusual behavior, or cost outliers and surfaces actionable alerts. | Supported in code / documentation gap | Code includes anomaly thresholds and trend/spike detection although this capability is not clearly surfaced in public documentation. | Expose anomaly detection operationally and validate alert thresholds/action routing. | SP + Astound | Delivered | Synthetic anomaly injection test | https://astound.systemprompt.io/documentation/enterprise-audit-observability | Thresholds are first-pass and will need tuning against real traffic in the first weeks. | Delivered - hourly spike detection (requests/cost/errors vs trailing-week hourly baseline), persisted so restarts cannot forget an incident, Slack-alerted on first detection, surfaced on the spend dashboard. | just e2e -- --grep @REQ-031 |  | 2026-08-25
REQ-032 | Automatic Provider Failover | As a Business, I shall be able to failover automatically to a secondary model provider when a primary provider is unavailable without application code changes, so that provider outages don't translate into application downtime or emergency engineering response | Gateway / Reliability | Global / Enterprise | Oleksandr Manatskyi | P2 – Medium | Provider outages don't translate into application downtime or emergency engineering response. | When the primary provider fails, eligible traffic automatically fails over to an approved secondary provider without application code changes. | Partial | Fallback/failover exists on provider errors, but proactive health-check-driven failover was not evidenced. | Run provider-failure tests and decide whether proactive provider health checks are required. | SP + Astound | Open | Provider outage/failure-injection test | https://astound.systemprompt.io/documentation/enterprise-roadmap | Needs secondary-provider fields on routes + error/health-triggered retry in core (~2-3 wks). Interim mitigation that works today: flipping a route's provider is a one-line config change. | Not delivered - and a correction to the earlier assessment: no automatic failover exists in the gateway dispatch path at all (what looked like fallback belongs to a different subsystem). | just e2e -- --grep @REQ-032
REQ-033 | Per-Consumer LLM Rate Limiting | As a Business, I shall be able to rate-limit LLM traffic per consumer, so that one team or runaway agent cannot exhaust org-wide provider quotas or internal budgets and degrade service for everyone else | Gateway / Reliability | Global / Enterprise | Oleksandr Manatskyi | P1 – High | One team or runaway agent cannot exhaust org-wide provider quotas or internal budgets and degrade service for everyone else. | Rate limits can be applied per agreed consumer boundary so one user/team/agent/application cannot exhaust shared provider capacity. | Supported | Tiered request rate limiting is supported; team/department-specific boundaries require confirmation. | Define consumer identity/scoping and validate isolation under load. | SP + Astound | Delivered | Load and rate-limit isolation test | https://astound.systemprompt.io/documentation/enterprise-safety-guardrails | Review the shipped quota sizes against expected traffic and tell us the numbers you want. Per-team limits await the Hub/team definition (REQ-006). | Delivered and now ENABLED - per-user hourly window (600 requests / $20) and per-organization daily window ($200) as a runaway backstop above the plan budgets, plus role-tier multipliers. | just e2e -- --grep @REQ-033 | DEC-001, DEC-004 | 2026-08-25
REQ-034 | Private / Self-Hosted Model Routing | As a Business, I shall be able to route requests to self-hosted or private cloud models for workloads that cannot leave the network boundary, so that data residency, regulatory, or security requirements are met without forgoing AI capability entirely | Gateway / Reliability | Global / Enterprise | Oleksandr Manatskyi | P2 – Medium | Data residency, regulatory, or security requirements are met without forgoing AI capability entirely. | Eligible workloads can be routed to self-hosted/private endpoints with no unintended public-provider egress. | Supported | Self-hosted/private routing and air-gapped patterns are supported. | Validate approved private endpoints, network controls, and no-egress scenarios. | SP + Astound | Delivered | Private endpoint / network-egress test | https://astound.systemprompt.io/documentation/enterprise-model-routing | For a no-egress guarantee pair this with network controls; we can run the residency test together. | Delivered - any OpenAI/Anthropic-compatible private endpoint is a config entry; private providers stay un-advertised to clients; routes are validated at boot. | just e2e -- --grep @REQ-034 |  | 2026-08-25
REQ-035 | A/B Model & Provider Testing | As a Business, I shall be able to A/B test model versions or providers on live traffic without application-layer changes, so that routing and procurement decisions are based on production evidence rather than benchmark claims or vendor marketing | Gateway / Reliability | Global / Enterprise | Oleksandr Manatskyi | P3 – Low | Routing and procurement decisions are based on production evidence rather than benchmark claims or vendor marketing. | Administrators can split eligible live traffic between model/provider variants and measure results without application code changes. | Gap | No percentage traffic splitting / experiment-assignment mechanism was evidenced. | Implement experiment traffic splitting and measurement if A/B testing remains in scope. | SP + Astound | Open | Traffic-split experiment test | https://astound.systemprompt.io/documentation/enterprise-roadmap | Moderate core change (~2 wks: split + sticky assignment + variant stamped into the audit row). P3 - propose deferring until a concrete A/B question exists. | Not delivered - routing is strictly first-match; no percentage split or experiment assignment exists. | just e2e -- --grep @REQ-035
REQ-036 | PII / PHI Detection & Redaction | As a Business, I shall be able to detect and redact PII/PHI in prompts and completions before they leave the org boundary or are persisted to logs, so that sensitive data exposure and regulatory violations are prevented at the gateway layer rather than relying on every application team to implement it independently | Data Governance / Security | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Sensitive data exposure and regulatory violations are prevented at the gateway layer rather than relying on every application team to implement it independently. | Configured sensitive-data categories are detected and redacted or blocked before external transmission and before persistence where required. | Partial | Email and credit-card detection/blocking are evidenced, but full PII/PHI coverage and completion-side redaction are not. | Define enterprise PII/PHI taxonomy and implement complete request/response redaction or blocking. | SP + Astound | Testing | PII/PHI redaction adversarial test | https://astound.systemprompt.io/documentation/enterprise-safety-guardrails | DECISION NEEDED: the required PII/PHI category list, and per category whether to redact or block. True in-flight redaction (rewrite before forwarding) is a scoped design item, not a toggle. | Partially delivered and now ENABLED - 34 credential patterns + entropy backstop on ingress; email, credit-card, SSN and E.164 phone detection both directions; SSNs masked in admin transcripts. Enforcement blocks rather than redacts in flight; no health-data (PHI) taxonomy. | just e2e -- --grep @REQ-036 | DEC-003
REQ-037 | Data Residency Routing | As a Business, I shall be able to enforce data residency by routing requests to region-specific or sovereign model instances based on data classification, so that customer or regulatory data never crosses a jurisdictional boundary it isn't permitted to cross | Data Governance / Security | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Customer or regulatory data never crosses a jurisdictional boundary it isn't permitted to cross. | Routing rules can enforce that classified workloads remain within the configured jurisdiction/region/sovereign endpoint. | Supported with policy validation | Regional/private/self-hosted routing provides the residency foundation; data-classification-to-route policy should be validated explicitly. | Define data-classification labels and enforce region/provider routing policies against them. | SP + Astound | Delivered | Regional routing / residency policy test | https://astound.systemprompt.io/documentation/enterprise-model-routing | Extend the classification taxonomy beyond these two flags whenever Astound defines its data-classification scheme - the enforcement seam is in place. | Delivered - provider/model YAML carries governance metadata (european, no_retain); routes declare requirements; the server refuses to boot or dispatch a route whose provider cannot satisfy them, and audits the decision. | just e2e -- --grep @REQ-037 |  | 2026-08-26
REQ-038 | Provider No-Train / No-Retain Policy Enforcement | As a Business, I shall be able to enforce that requests are only routed to model providers with a contractually agreed no-train / no-retain clause when handling classified data, so that submitted prompts and completions cannot be used by a provider to train or improve their models in violation of the org's data agreements | Data Governance / Security | Global / Enterprise | Oleksandr Manatskyi | P2 – Medium | Submitted prompts and completions cannot be used by a provider to train or improve their models in violation of the org's data agreements. | Policy can prevent classified requests from being routed to providers that do not satisfy the configured no-train/no-retain contractual requirement. | Gap | No policy link between data classification and provider contractual no-train/no-retain terms was evidenced. | Add provider contractual-policy metadata and enforce it in routing decisions for classified data. | SP + Astound | Delivered | Classified-data provider-policy test | https://astound.systemprompt.io/documentation/enterprise-model-routing | The contractual flags are config - keep them in step with the actual provider agreements. | Delivered - same mechanism as REQ-037: governance.no_retain on the provider/model + requires on the route means classified traffic can only reach contractually no-retain providers, enforced at boot and at dispatch. | just e2e -- --grep @REQ-038 |  | 2026-08-26
REQ-039 | Prompt & System Message Versioning / Rollback | As a Business, I shall be able to version and roll back prompts and system messages independently of application deploys, so that a prompt-level fix or regression can be corrected without requiring every consuming application to redeploy | Configuration / Lifecycle | Global / Enterprise | Oleksandr Manatskyi | P2 – Medium | A prompt-level fix or regression can be corrected without requiring every consuming application to redeploy. | Prompt/system-message versions are centrally versioned, deployable, auditable, and rollbackable independently of application release cycles. | Gap | Current source analysis indicates the older prompt/playbook versioning subsystem was removed; no first-class prompt rollback primitive is evidenced. | Design a first-class prompt configuration/version lifecycle if independent rollback is required. | SP + Astound | Open | Prompt version deploy + rollback test | https://astound.systemprompt.io/documentation/enterprise-roadmap | Design-first item (~2-3 wks build after sign-off): versioned template object, activation pointer (rollback = repoint), audit of which version served which request. Treat together with REQ-040. | Not delivered - no prompt registry exists; system-prompt overrides have no version history, so rollback today means redeploying config. | just e2e -- --grep @REQ-039
REQ-040 | Central Prompt Template Distribution | As a Business, I shall be able to centrally manage and distribute prompt templates across consuming applications, so that a security or quality fix can be applied once rather than requiring coordinated changes across every application team | Configuration / Lifecycle | Global / Enterprise | Oleksandr Manatskyi | P2 – Medium | A security or quality fix can be applied once rather than requiring coordinated changes across every application team. | Approved prompt templates can be centrally managed and distributed to consuming applications with controlled updates/revocation. | Partial | Central signed-manifest distribution exists for skills/plugins, but prompt templates are not evidenced as a distinct first-class lifecycle object. | Define whether prompt distribution will use skills or needs a dedicated prompt-template registry. | SP + Astound | In progress | Central template publish/update/revoke test | https://astound.systemprompt.io/documentation/enterprise-roadmap | That lifecycle object is the REQ-039 design - one piece of work, not two. | Partially delivered - Ed25519-signed, centrally revocable distribution (the skills channel) can carry prompt content today; it is not a versioned template object with parameters and rollback. | just e2e -- --grep @REQ-040
REQ-041 | Pre-Execution Tool Governance | As a Business, I shall be able to enforce permission, secret-exposure, and rate-limit checks on every tool call an agent makes before the underlying action executes, so that a misconfigured or compromised agent cannot take an unauthorized action just because it has model access | MCP / Tool & Agent Governance | Global / Enterprise | Oleksandr Manatskyi | P1 – High | A misconfigured or compromised agent cannot take an unauthorized action just because it has model access. | Every agent/tool invocation passes required authorization, secret-exposure, safety, and rate-limit checks before the underlying action executes. | Supported | Governance checks are enforced synchronously before dispatch and denied calls are audited. | Validate every relevant tool path goes through pre-execution governance and audit. | SP + Astound | Delivered | Unauthorized tool-call negative test | https://astound.systemprompt.io/documentation/enterprise-tool-governance | Run the negative tests in the evidence pack to confirm enforcement in your environment. | Delivered and now ENABLED - the four-stage pre-execution chain (scope check, secret scan, blocklist, rate limit) runs synchronously before every tool dispatch, first-deny-wins, every decision audited with trace linkage. It had been deliberately off during evaluation. | just e2e -- --grep @REQ-041 |  | 2026-08-25
REQ-042 | Governed MCP Server Registry | As a Business, I shall be able to register, authenticate, and govern every MCP server an agent can connect to, with a signed and centrally revocable allowlist, so that tool access for autonomous agents is controlled with the same rigor as model access | MCP / Tool & Agent Governance | Global / Enterprise | Oleksandr Manatskyi | P1 – High | Tool access for autonomous agents is controlled with the same rigor as model access. | Every MCP server is centrally registered, authenticated, allowlisted, auditable, and revocable before agents can connect to it. | Supported | MCP allowlisting, authentication/scopes, auditability, and central revocation are evidenced. | Validate MCP lifecycle operations, revocation propagation, and emergency kill-switch behavior. | SP + Astound | Delivered | MCP registration/auth/revocation test | https://astound.systemprompt.io/documentation/enterprise-tool-governance |  | Delivered - declarative MCP registry with per-server auth scopes/audience, plan-based entitlement, immediate revocation (suspend the org or disable in config), and token-level revocation. | just e2e -- --grep @REQ-042 |  | 2026-08-25
REQ-043 | Tool Schema Validation | As a Business, I shall be able to validate tool schemas at registration time, so that a malformed or incompatible tool integration fails at startup or deployment rather than failing during a live customer interaction | MCP / Tool & Agent Governance | Global / Enterprise | Oleksandr Manatskyi | P1 – High | A malformed or incompatible tool integration fails at startup or deployment rather than failing during a live customer interaction. | Tool schemas are validated during registration/deployment and invalid or incompatible integrations fail before live runtime execution. | Supported | Tool/schema validation at registration/connect time is evidenced so invalid integrations can fail before live execution. | Test malformed/incompatible tool schemas in CI/deployment and verify fail-fast behavior. | SP + Astound | Delivered | Invalid schema registration/deployment test | https://astound.systemprompt.io/documentation/enterprise-tool-governance | Add JSON-Schema meta-validation (~1 wk) if malformed-schema CI tests are a hard requirement. | Delivered with a stated caveat - registration fails fast on missing/invalid manifests and schema sync; tool input schemas are captured but not meta-validated against JSON Schema (a well-formed-but-wrong schema passes). | just e2e -- --grep @REQ-043 |  | 2026-08-25
REQ-044 | User Awareness | The system must enforce dynamic access control based on the user's active session context — including project, role, and permissions — to determine which MCP servers, models, and knowledge sources the user can access. | Identity & Access / Context | Enterprise / Core / Commerce | Jay Dave | P0 – Critical | Ensures that AI access is dynamically constrained by the user's current project context, role, and permissions rather than relying on static platform-wide access. | Two users with different project/role/permission contexts receive different authorized sets of MCP servers, models, and knowledge sources; unauthorized resources are not discoverable or callable, and access decisions are auditable. | Gap — stakeholder identified | Identified as missing from the current SystemPrompt.IO scope in the stakeholder review. | Define the session-context model and implement/enforce context-aware authorization across MCP servers, models, and knowledge-source access. | SP + Astound | Open | Role/project/session matrix test + negative access-control test |  | Source: new technical stakeholder input. Missing SystemPrompt.IO requirement.
REQ-045 | Conversation History | Users and their managers must be able to search and audit the user's full AI interaction history, including prompts, responses, tools used, and timestamps, through a secure identity-aware interface. | Audit / Conversation History | Enterprise / Core / Commerce | Jay Dave | P1 – High | Provides transparent, identity-aware review of AI activity for individual users and authorized managers, supporting auditability, investigations, coaching, and governance. | An authenticated user can search their own AI interaction history; an authorized manager can search the history of permitted users; results include prompts, responses, tools used, and timestamps; unauthorized users cannot access another user's history. | Gap — stakeholder identified | Identified as missing from the current SystemPrompt.IO scope in the stakeholder review. | Provide a secure searchable interaction-history interface with identity-aware authorization and manager-level audit permissions. | SP + Astound | Open | User/manager history search test + unauthorized access test |  | Source: new technical stakeholder input. Missing SystemPrompt.IO requirement.
REQ-046 | Knowledge Accuracy SLO | The external knowledge platform must achieve a knowledge-retrieval accuracy SLO greater than 70% precision@5 for the agreed benchmark/use-case set. | Knowledge Platform / Quality | External Knowledge Platform / Core / Commerce | Jay Dave | P1 – High | Establishes a measurable quality threshold for enterprise knowledge retrieval used by AI workflows. | A representative benchmark set is defined and repeatable evaluation demonstrates precision@5 greater than 70% for the agreed scope. | External to SystemPrompt.IO | Explicitly identified by the stakeholder as a Knowledge Base requirement outside SystemPrompt.IO's core governance layer. | Define the benchmark corpus, evaluation methodology, ownership, and quality-monitoring process in the external knowledge platform. | SP + Astound | Open | Knowledge retrieval benchmark using precision@5 |  | Source: new technical stakeholder input. External Knowledge Base requirement; not a SystemPrompt.IO core product gap.
REQ-047 | Enterprise RAG Pipeline | The external knowledge platform must provide a RAG pipeline capable of retrieving governed enterprise knowledge from Jira, Confluence, GitHub, and Salesforce for AI use cases. | Knowledge Platform / RAG | External Knowledge Platform / Core / Commerce | Jay Dave | P1 – High | Provides the contextual enterprise knowledge required for Core and Commerce AI workflows to generate grounded responses and actions. | Content from Jira, Confluence, GitHub, and Salesforce can be ingested/indexed according to the agreed architecture and retrieved through the RAG pipeline with traceable source references and access controls. | External to SystemPrompt.IO | Explicitly identified by the stakeholder as a Knowledge Base capability handled through external systems such as MCP servers and vector databases. | Design and implement the external RAG architecture, ingestion/indexing pipelines, retrieval services, and integration boundaries with SystemPrompt.IO. | SP + Astound | Open | End-to-end RAG retrieval test across all required sources |  | Source: new technical stakeholder input. External Knowledge Base requirement.
REQ-048 | Enterprise Knowledge Source Integrations | The external knowledge platform must provide governed integrations with Salesforce, Confluence, and Jira for ingestion and/or retrieval of enterprise knowledge. | Knowledge Platform / Integrations | External Knowledge Platform / Core / Commerce | Jay Dave | P1 – High | Enables AI workflows to access the principal enterprise systems of record required by the target solution. | Salesforce, Confluence, and Jira integrations authenticate successfully, respect source-system permissions, retrieve the agreed data scope, and expose source lineage for retrieved content. | External to SystemPrompt.IO | Explicitly identified as an external Knowledge Base requirement rather than a SystemPrompt.IO core capability. | Define and implement the required source connectors/MCP integrations, permission model, refresh strategy, and operational ownership. | SP + Astound | Open | Source integration connectivity + permission propagation test |  | Source: new technical stakeholder input. External Knowledge Base requirement.
REQ-049 | Knowledge Graph for Semantic Queries | The external knowledge platform must support a knowledge graph or equivalent semantic relationship layer to enable semantic queries across enterprise entities and their relationships. | Knowledge Platform / Semantic Layer | External Knowledge Platform / Core / Commerce | Jay Dave | P2 – Medium | Supports relationship-aware queries that cannot be reliably answered through isolated document retrieval alone. | The platform can represent agreed enterprise entities/relationships and answer the defined semantic query scenarios with traceable source relationships. | External to SystemPrompt.IO | Explicitly identified by the stakeholder as a Knowledge Base requirement outside SystemPrompt.IO's core. | Define target graph use cases, ontology/entity model, source mapping, and integration with retrieval/agent workflows. | SP + Astound | Open | Semantic query test against agreed entity/relationship scenarios |  | Source: new technical stakeholder input. External Knowledge Base requirement.
REQ-050 | Use Case Examples Library | The external knowledge platform must maintain a searchable library of proven AI use-case examples and workflows that users and teams can reuse as implementation references. | Knowledge Platform / Enablement | External Knowledge Platform / Core / Commerce | Jay Dave | P2 – Medium | Accelerates adoption by allowing teams to discover and reuse proven patterns rather than repeatedly designing workflows from scratch. | Authorized users can search and retrieve approved use-case examples containing sufficient context to understand the workflow, intended users, systems involved, and expected outcome. | External to SystemPrompt.IO | Explicitly identified by the stakeholder as an external Knowledge Base requirement. | Define the use-case taxonomy, metadata, ownership/curation process, and publishing/search mechanism. | SP + Astound | Open | Use-case discovery and retrieval test |  | Source: new technical stakeholder input. External Knowledge Base requirement.
REQ-051 | User-Facing Searchable Conversation History | The external knowledge platform or supporting application must provide a user-facing capability to search previous AI conversations when those conversations are intended to become part of the reusable knowledge experience. | Knowledge Platform / Conversation History | External Knowledge Platform / Core / Commerce | Jay Dave | P1 – High | Allows users to recover prior AI work and reuse previous decisions, answers, and context as part of the wider knowledge experience. | An authenticated user can search and retrieve their authorized historical conversations through the user-facing knowledge experience while respecting retention and access-control policies. | External to SystemPrompt.IO | The stakeholder explicitly separated user-facing searchable conversation history as a Knowledge Base requirement, while REQ-045 covers secure SystemPrompt audit/search requirements. | Define which conversation data is exposed to the knowledge layer, retention/indexing rules, identity enforcement, and integration with the audit history capability. | SP + Astound | Open | User-facing conversation search + authorization test |  | Source: new technical stakeholder input. External Knowledge Base requirement. Related to REQ-045 but retained separately because the source assigns it to the knowledge platform.
REQ-052 | Context-Aware Knowledge Retrieval Access Control | The external knowledge platform must enforce context-aware access control during knowledge retrieval so that users and AI agents only retrieve content permitted by the user's identity, project, role, permissions, and source-system entitlements. | Knowledge Platform / Access Control | External Knowledge Platform / Core / Commerce | Jay Dave | P0 – Critical | Prevents enterprise knowledge from being exposed through RAG or semantic retrieval to users who would not be authorized to access it in the source or current project context. | Retrieval results are filtered using the agreed identity/project/role/permission context; unauthorized documents/entities are never returned; permission changes propagate according to the agreed policy; denied access is auditable. | External to SystemPrompt.IO | Explicitly identified as a Knowledge Base requirement outside SystemPrompt.IO's core governance layer, but it must interoperate with the session/context authorization model in REQ-044. | Design permission propagation and retrieval-time filtering across vector/graph/MCP layers and define the context contract shared with SystemPrompt.IO. | SP + Astound | Open | Cross-role/project retrieval test + unauthorized content negative test |  | Source: new technical stakeholder input. External Knowledge Base requirement. Related to REQ-044.
REQ-053 | ADFS SSO Support | SystemPrompt.IO must support authentication through Astound Active Directory Federation Services (ADFS) SSO. Active Directory groups must be usable to authorize users and map different permissions such as admin, regular user, project membership, and other access groups. | Identity & Access / SSO | Enterprise / Core / Commerce | Sergey Kubrakov | P0 – Critical | Allows SystemPrompt.IO to use the enterprise identity and group-management model rather than maintaining a separate identity lifecycle and permission structure. | A user can authenticate to SystemPrompt.IO through ADFS SSO; relevant AD/ADFS group claims are received and mapped to configured SystemPrompt roles/project permissions; users without approved group membership are denied access; changes to group membership are reflected according to the agreed synchronization/session policy. | Requires validation / implementation | ADFS-specific SSO and AD group-to-SystemPrompt authorization mapping must be validated against the deployed solution. | Validate supported ADFS protocol/claim integration and implement group-to-role/project/permission mapping required by Astound. | SP + Astound | Open | ADFS login test + group-claim mapping + access/deprovisioning test |  | Source: new technical stakeholder input. The source reused REQ-045; renumbered to REQ-046 to maintain unique backlog IDs.

## Decisions
ID | Topic | Related REQs | Question for Astound | Why it matters / what it blocks | Options & our recommendation | Owner | Status | Decision | Date decided | Notes
DEC-001 | Team / Project definition | REQ-006, REQ-010, REQ-013, REQ-033 | How do Astound define 'team' and 'project'? Provide 2-3 concrete examples from Core/Commerce expressed as a data structure: does a user belong to one team or many; does a project grant access or is it only a reporting label; how do Hub, team and project nest under an organization? | Blocks per-team/project analytics drill-down, budgets, hard cutoffs, and rate limits. Hub is agreed as a geographic grouping; team/project are the missing layers beneath it. | Recommend: user belongs to exactly one team (like organization today, keeps queries and authz simple); project as a request-level label for reporting only, not entitlement. Once examples land we design the schema against them (~1-2 wks to implement the dimension end to end). | Astound | Awaiting Astound
DEC-002 | Identity source of truth + external platform mapping | REQ-008, REQ-023, REQ-007 | What is the authoritative identity provider going forward - Salesforce, Okta, Entra, GitHub? And which external platforms hold user activity we must correlate (which Git host counts as the SCM of record), with what API access, and what is the mapping rule from an external identity (e.g. commit-author email, SCM login) to a platform user? | Blocks full commit analytics (commits outside Claude Code are invisible today), automated offboarding beyond Salesforce, and any IDE/SCM productivity correlation. Only Salesforce SSO is wired today, including automatic deprovisioning. | Recommend: keep Salesforce as IdP if that is the corporate directory (offboarding reconciliation already live); if Okta/Entra is the real directory, say so now - that is a new connector and re-opens SCIM as the right channel. For SCM: name one host + grant webhook/API access; verified-email mapping to platform users, with a manual override table for mismatches (~1 wk after the decision). | Astound | Awaiting Astound
DEC-003 | Safety policy - what 'safety' means for Astound | REQ-030, REQ-036 | Confirm the category list and, per category, block vs audit-only. Is PHI (health data) in scope? Is toxicity/brand-risk classification required (that needs a classifier, not pattern heuristics)? Should in-flight redaction (rewrite before forwarding) replace blocking for any category? | The scanners are live with our defaults: BLOCK jailbreak, credit cards, SSNs on ingress; secrets and SSNs on buffered egress; email/phone audit-only. Until Astound signs this off, enforcement reflects our judgement, not their policy. | Recommend: ratify the current block list as v1; add PHI only if regulated health data actually transits the gateway; treat toxicity/brand-risk as a phase-2 item needing a model-based classifier (separate estimate). Redaction-instead-of-block is a scoped design item, not a toggle. | Astound | Awaiting Astound
DEC-004 | Quota sizes | REQ-033 | Review the live first-pass quotas against expected traffic: 600 requests + $20 per user per hour; $200 per organization per day (runaway backstop above the monthly plan budgets). What numbers do you want? | Too tight throttles legitimate work; too loose defeats the runaway-agent backstop. Only Astound knows expected per-seat intensity. | Recommend: run 2 weeks of real traffic, then set user/hour at ~3x observed p95 and org/day at ~2x observed peak day. We can produce the observed numbers from the dashboard on request. | SP + Astound | Awaiting traffic data
DEC-005 | Quality baseline for model comparison | REQ-017, REQ-018 | Define what 'quality' means: an agreed eval set of representative tasks (with expected outcomes or a grading rubric) against which providers/models can be scored. | Blocks quality-normalized provider cost comparison and any automatic optimal-model routing. Cost/latency sides are already measured; quality has no data source without this. | Recommend: start with 20-50 real tasks from Core/Commerce workloads, graded pass/fail; we run them per provider/model and join the scores to the existing cost/latency telemetry. Decide later whether routing recommendations live in the gateway or an eval layer. | Astound | Awaiting Astound
DEC-006 | Observability export target | REQ-028 | Name the target stack: Datadog, Splunk, or LGTM (Grafana). Provide the ingestion endpoint + credentials for the chosen one. | OTLP ingest and the live audit stream exist; nothing pushes to an external SIEM/APM yet. Building all three exporters unprompted is waste. | Recommend: whichever the on-call team already lives in. Datadog/LGTM = OTLP exporter (~1-2 wks); Splunk = HEC JSON push (~1 wk). | Astound | Awaiting Astound
DEC-007 | Compliance regime for the audit trail | REQ-026 | Which standard must the audit trail satisfy (SOC 2, ISO 27001, GDPR-only, sector-specific)? And what retention window is required for ai_requests? | The trail is complete but append-only by convention, not mechanism, and currently unbounded. The regime picks the hardening: DB-role REVOKE (cheap), hash-chaining, or WORM export - and the retention sweep we must add. | Recommend: DB-role REVOKE UPDATE/DELETE + a defined retention window covers SOC 2/ISO in practice (~1 wk); hash-chaining or WORM only if an auditor explicitly requires tamper-evidence. | Astound | Awaiting Astound
DEC-008 | Per-key budgets - real use cases | REQ-022 | What are you actually trying to achieve per key? Individual USER budgets are already enforced (per-user hourly dollar/request quotas; every key inherits its owner's limits; org caps above). Do you have a case where ONE identity needs MULTIPLE keys with different budget/rate/model policy per key? | Determines adapt vs build. If each application/customer gets its own platform account, per-user enforcement already gives per-app budgets and the requirement is met as-is. Many-keys-per-identity policy is a ~2-week core change. | Recommend: send the concrete scenarios (which systems hold keys, what limits each needs). Default position: model each app/consumer as its own account and close the row without new build. | SP + Astound | Awaiting use cases

## Objectives
Stage | ID | Objective | Owner | Why it matters | Definition of done | Current state | Next action | Metric (updated nightly by systemprompt) | Latest value | Last updated | Status | Notes
Stage 0 - Infrastructure | OBJ-001 | Stand up the Astound instance with a one-command deploy | SP + Astound | Astound owns setting up the infrastructure; a deploy that needs env flags or hand-holding cannot be run daily by their team. | Astound can take the repo from HEAD to live on their target environment with a single command (or CI/CD on push), no prompts, no env-var incantations, and the command exits green only when the site answers healthy. | systemprompt's Fly deploy works end to end (~20 min) but carries three frictions: an env flag for a never-published optional artifact, migrations run with the previous binary (bricks the first deploy after a core config change), and no post-deploy health gate (app 503s ~2 min during boot, command exits green regardless). | systemprompt: remove the three frictions from the recipe, then hand Astound the runbook for their environment; Astound: name the target environment and run the deploy themselves. | Commands to live; wall-clock minutes; manual interventions; exit-reflects-health (Y/N) | 1 cmd + 1 env flag; ~20 min; 0-2 interventions; exit does NOT reflect health | 2026-08-26 | Blocked | Nightly row updated by systemprompt. Astound leads; systemprompt owns the supporting/enabling work.
Stage 0 - Infrastructure | OBJ-002 | Measure and bound gateway latency overhead | SP + Astound | Every governed call transits systemprompt compute (auth, governance, quota, safety, audit). Astound must be able to test that the deployment does not add material latency to their flows. | A nightly-published overhead figure - p50/p95/p99 of (total latency minus upstream provider latency) on real traffic plus a synthetic probe - against an agreed budget (proposed: p95 <= 150ms buffered, <= 50ms to first streamed byte), with regression alerts. | Overhead is currently UNMEASURABLE: total latency_ms is recorded but upstream provider time is not captured separately, and the newly enabled governance/safety stages are unquantified. | systemprompt: record upstream_latency_ms in the audit row (small core change), add the nightly synthetic probe job, surface p50/p95/p99 on the dashboard and here; Astound: run load tests against their instance and agree the latency budget. | Gateway overhead ms p50/p95/p99 (production + probe); regression vs previous night | UNMEASURED - instrumentation gap | 2026-08-26 | Blocked | Budget proposal pending Astound agreement. Astound leads; systemprompt owns the supporting/enabling work.
Stage 0 - Infrastructure | OBJ-003 | Load-test the infrastructure at expected traffic | Astound | Deployability and speed are only proven under load: quotas, the governance chain, and the audit write path all sit on the request path and must hold at rollout concurrency. | A load test at expected peak concurrency (seats x realistic request rate) against the Astound instance passes: no 5xx from the gateway itself, quota/budget guards behave, latency stays inside the OBJ-002 budget, and the DB connection pool does not saturate. | Never run against a production-shaped deployment. | Astound: define expected peak (seats, req/min) and run the test (hey/k6 scripts can be provided); systemprompt: fix whatever it finds. | Peak RPS sustained; gateway 5xx count; p95 latency under load; DB pool headroom | Not yet run | 2026-08-26 | Not started | Depends on OBJ-001 (an environment to test).
Stage 0 - Infrastructure | OBJ-004 | Wire monitoring and alerting to Astound's stack | SP + Astound | The infra is not operable by Astound until its alerts (budget, anomaly, deprovisioning) and telemetry land where their on-call actually looks. | Budget/anomaly/offboarding alerts arrive in an Astound-owned channel, and gateway telemetry flows to their chosen observability stack (DEC-006) with a dashboard their team can read. | Alerts currently post to systemprompt's Slack; telemetry export target undecided (Datadog/Splunk/LGTM - see Decisions DEC-006). | Astound: name the stack and the alert channel; systemprompt: build the exporter (~1-2 wks) and repoint the alerts. | Alert delivery verified (Y/N); exporter events/day reaching the stack | Not wired | 2026-08-26 | Blocked | Astound leads; systemprompt owns the supporting/enabling work. Blocked on DEC-006 (observability target).
Stage 1 - MVP (RAG system) |  | (objectives to be defined once Stage 0 closes)

## Definitions
Priority | Definition | Status | Definition
P0 – Critical | Required for security, controlled rollout, or production readiness. | Open | Requirement captured; validation not yet completed.
P1 – High | Required for effective enterprise rollout, governance, or measurable adoption. | Validating | Capability is being tested against the requirement.
P2 – Medium | Valuable for optimization or impact measurement but not an initial rollout blocker. | Gap | Requirement is not currently satisfied.
P3 – Low | Future enhancement with limited impact on initial implementation. | Closed | Requirement has been validated and accepted.
Owner | Meaning
SystemPrompt | Ed / SystemPrompt
Astound | Astound stakeholders
Engineering | Astound engineering
SP + Astound | Joint: SystemPrompt leads with Astound input
SP + Engineering | Joint: SystemPrompt + Astound engineering

## Summary
SystemPrompt × Astound — Requirements Summary
Live rollup — figures recalculate from the other tabs. Master data: systemprompt-astound repo (requirements/*.csv); Objectives metrics updated nightly.
Status | Count | Meaning | Priority | Count | Programme | Value
Delivered | 27 | Built, evidenced, live — accept when ready | P0 | 2 | Decisions awaiting Astound | 8
Testing | 2 | Enabled with defaults — needs Astound sign-off | P1 | 28 | Stage 0 objectives outstanding | 4
In progress | 2 | Being extended | P2 | 10 | Requirements delivered % | 63%
Blocked | 8 | Waiting on a decision (see Related decision column) | P3 | 3 | Docs | https://astound.systemprompt.io/documentation
Open | 4 | Not built — scoped on the roadmap | Total | 43 | Production | https://astound.systemprompt.io
Total | 43